## Bugsheet (Discon.)
S No. | Environment Detail | Team comments | Label | Screen Name | Defect Description | Expected result | Attachments | Status | Retesting Status | Retesting Remarks (If any)
1 | Android Samsung Galaxy S22 Ultra |  | Bug (Functionality) | Your Account | The name field does not have the validations for the characters limit | The "Name" field should have a character limit validation. Users should not be able to enter more than the specified maximum number of characters | https://drive.google.com/file/d/1D-y0InFNcQFxhaqZ6VVvnmOVuOrgAOds/view?usp=sharing | Done
2 | Android Samsung Galaxy S22 Ultra |  | Bug (Functionality) | Your Account | The alert message displayed does not specify which field it is referring to, which can cause confusion for the user. | The alert message should clearly indicate the specific field it applies to, such as: “Name cannot exceed 50 characters” or “Password cannot be the same” | https://prnt.sc/H1IMD-hKTVZ_ | Done
3 | Android Samsung Galaxy S22 Ultra | Khoa: You're supposed to paste it into a website. And on my device, it is also clickable. K: This should be clickable as a 1 time click. Shorten it if possible | Critical Bug | Add a New Partner | When attempting to add a new partner by sharing the invitation link, the link is not clickable and does not function as a hyperlink, preventing the user from accessing the intended page. | The invitation link should be clickable and function as a hyperlink, directing the user to the appropriate page upon clicking. | https://prnt.sc/D5-2Cu4cZx29 | Not Done Yet
4 | Android Samsung Galaxy S22 Ultra | Khoa: This is an old bug. | Bug (Functionality) | Add Journal | On the Add Journal home,While adding a new Journal the Descriptions are not visible on the Journal Page | The journal entry should display both the title and description on the Journal Page, allowing users to see the full details of their entry. | https://drive.google.com/file/d/1DMRSW2PO742Ir4BI_5BHco9ktPEbx01A/view?usp=sharing | Not Done Yet
5 | Android Samsung Galaxy S22 Ultra | Khoa: I tested and the default color is white, can't replicate this. Dev: You can change the color from the toolbar by default color is white. K: as long as the default colour in every line is white. disregard this | Bug (Functionality) | Rules | In the Rules section, the text entered by the user is mostly the same color as the background, making it difficult or impossible to read. | The text color should contrast with the background color to ensure readability. Users should be able to clearly see the text they have entered. | https://prnt.sc/DYm8g54KMjeW | Not Done Yet
6 | Android Samsung Galaxy S22 Ultra | Khoa: It's intended behavior. | Bug (Functionality) | Rules | Unable to add the signature for the Partner B K: B is the partner's slot | Users should be able to successfully add and save a signature for Partner B, which should be visible upon submission. | https://drive.google.com/file/d/1DdD0R1WY4ChqXucfUS0GnXXL4-L8Q-S8/view?usp=sharing | Not Doing
7 | Android Samsung Galaxy S22 Ultra | Khoa: Minor usability bug | UI/UX Bug | Notes | When attempting to write a note in the Notes section, the text is cropped, making only the top half of the text visible while the bottom half is hidden. | The entire text should be visible as the user types in the Notes section, without any cropping at the bottom. The text area should dynamically adjust to show all entered content. | https://prnt.sc/V4MagSxutnHg | Done
8 | Android Samsung Galaxy S22 Ultra | Khoa: Minor usability bug | Bug (Functionality) | Notes | The text is overlapping over the Edit icon | The text should be properly aligned and spaced so that it does not overlap with the Edit icon | https://prnt.sc/uVhmZ--rtYK- | Done
9 | Android Samsung Galaxy S22 Ultra | Khoa: screen overflow bug | UI/UX Bug | Dashboard | When the "When" dropdown is opened, the dropdown arrow goes underneath the menu, making it partially obscured | The dropdown arrow for the "When" field should remain visible and positioned outside the dropdown menu. | https://drive.google.com/file/d/1E0H3-xqEcpmQ_jXd4zv-Zfabq7toSkBi/view?usp=sharing | Not Done Yet
10 | Android Samsung Galaxy S22 Ultra | Khoa: White one is for free users, and yellow is for premium users. Dev: User is already only permission is locked due to solo user tab customisation is opened K: Resolved due to no more free premiuim | Bug (Functionality) | Profile | The Premium icon is displayed on the profile image of users who do not have a premium account. This could mislead users into thinking they have premium access when they do not. | The Premium icon should only be displayed on the profile image if the user has a premium account. Non-premium accounts should not show this icon. | https://drive.google.com/file/d/1E63SayS41eRzpDFuYutfVXQhOyHh2hli/view?usp=sharing | Done
11 | Android Samsung Galaxy S22 Ultra |  | Bug (Functionality) | Feedback | The feedback section allows users to submit feedback even when the Name, Title, and Feedback fields are left blank. This could lead to incomplete or unhelpful feedback entries in the system. | The feedback form should require that the Name, Title, and Feedback fields are filled out before submission. If any of these fields are blank, an error message should appear, prompting the user to complete all required fields. | https://drive.google.com/file/d/1ELMci8RFVZK8Ju2K3aYmoBb6CBahTlpY/view?usp=sharing | Done
12 | Google Chrome Macbook Air M2 Chip | Khoa: PLease don't test the website, since the website is undergoing a redesign. | UI/UX Bug | https://www.binded.app/goodtoknow | In the website's "About Us" section, the content is positioned behind the main container, causing part of the information to be hidden and inaccessible to users. | The "About Us" content should be fully visible within the container, properly aligned, and accessible to the user. | https://www.loom.com/share/3a6a7f0233b549ddac4c69f52c6729b8 | Not Doing
13 | iPhone 14 Pro Max & Samsung Galaxy S22 Ultra | Khoa: Please add a section about how to reproduce this bug. Dev: Can you please explain about this specific case K: I had a report from a customer who had this issue. it was resolved once they closed and reopened the app | UI/UX Bug | Partners | The users QAmohan98@gmail.com and testingteam1996@gmail.com are configured as partners within the system, yet they are not being displayed as partners on the relevant interface. | Both users, QAmohan98@gmail.com and testingteam1996@gmail.com, should be visible as partners in the partner list. | https://drive.google.com/file/d/1EX8CS_DomoNnAbJeiPGrXzTFSyMYXrm8/view?usp=sharing | Not Done Yet
14 | iPhone 14 Pro Max & Samsung Galaxy S22 Ultra | Khoa: Can' see the differences. Dev: Can you please provide both screen shots we can't find difference we are checked on Redmi Note 8 and i phone 11 pro | UI/UX Bug | Account | The logo for "Permissions" appears differently on iOS and Android devices, resulting in an inconsistent user experience across platforms. | The "Permissions" logo should appear identical across both iOS and Android platforms, maintaining brand consistency. | https://prnt.sc/SH32WynXmPcy | Not Doing
15 | iPhone 14 Pro Max & Samsung Galaxy S22 Ultra | Khoa: Ok | Critical Bug | Journal - Update Journal |  | The file located at the specified index (index 1) should be deleted, and the other files should remain unaffected. | https://drive.google.com/file/d/1EdRAh59C-HefGBUyvL23-CBjvfW4uOFt/view?usp=sharing | Done
16 | Android Samsung Galaxy S22 Ultra | Khoa: Normal behavior. Count are resetted at a specific count not 0. | Bug (Functionality) | Input Tracker | In the input tracker feature, clicking the "Reset" button should reset the count to zero. However, the count remains unchanged, failing to reset as expected. K: in a countdown, if you are counting down from 10 days, it will start from 10 and count downwards to 0. The reset will be back to 10 days. | The count should reset to zero upon clicking the "Reset" button. | https://drive.google.com/file/d/1EmgtWvZh0zEH_vWSs295-5HUO-RgoOZb/view?usp=sharing | Not Doing
17 | iPhone 14 Pro Max | Khoa: Good idea, I'll note it down. | Bug (Functionality) | Permissions | When updating permissions, no success message or alert is provided to indicate that the changes were successfully saved. This lack of confirmation can lead to uncertainty about whether the update was processed correctly. | A success message or alert should be displayed to confirm that the permissions have been updated successfully. | https://drive.google.com/file/d/1jiSRQVHQaQoWf_P50FXIBF2WSIg8UtMc/view?usp=sharing | Done
18 | iPhone 14 Pro Max | Khoa: Minor bug | Bug (Functionality) | Reset Password | On the reset password screen, when a user enters an incorrect OTP, an unclear or generic alert message is shown instead of a specific message informing the user that the OTP is incorrect. This could lead to confusion about the error and how to proceed. | A clear and specific alert message should be displayed, such as "Incorrect OTP. Please try again." | https://prnt.sc/gXmtjqY8JNDW | Done
19 | iPhone 14 Pro Max |  | Bug (Functionality) | Reset Password | "No Record Found" Alert Below Email Field Does Not Disappear After Entering a Registered Email Address | The "No Record Found" alert should automatically fade or disappear when a registered email address is entered. | https://drive.google.com/file/d/1yvnoLJN1SeEKBnFfmqNMsvji8V4uX_Jv/view?usp=sharing | Done
20 | iPhone 14 Pro Max | Khoa: Minor bug | UI/UX Bug | Login Screen | Login with Google, Apple and Email logo is not aligned | The logo should be aligned | https://prnt.sc/inwS7lOu7osF | Done
21 | iPhone 14 Pro Max | Khoa: Yes, Update about a smart button to solve this is in pending. | Bug (Functionality) | Login Screen | When the user starts typing in the Confirm Password field, the keyboard pops up. However, the text being typed is not visible to the user. | The Confirm Password field should remain visible above the keyboard so the user can see what they are typing. | https://drive.google.com/file/d/18QmPbMEsDBzUrKteVwXQTqUWuKm_n-Vo/view?usp=sharing | Not Done Yet
22 | iPhone 14 Pro Max | Khoa: I suspect it's because of bad internet connection QA: No. This is happenening frequently for me K: Jaya please investigate and fix Dev: I have checked this issue. It's because of low internet connection. When my network connectino is good it's not replicated and after that i am testing with poor internet then it's happened | Critical Bug | Login Screen | Occasionally, when the user navigates to the OTP screen, the loader spins indefinitely, preventing the OTP field or submit button from being accessible. This issue does not happen every time, but when it does occur, it blocks the user from moving forward, resulting in a poor user experience. | The loader should stop after a short period, allowing the user to input their OTP and proceed. | https://drive.google.com/file/d/1Z5BIXkkp1O_NxXp-Nj9mstykt6X3I7k9/view?usp=sharing | Not Done Yet
23 | Oppo Reno 8T | Khoa: I suspect it's because of bad internet connection, but it happens too often. | Critical Bug | Settings - Your Account | Looping screen when tapping the profile image. | No looping. | Loop + Unsaved changes | Not Done Yet
23 | Oppo Reno 8T | Dev: I am checked this bug on Wifi but can't replicate this. | Bug (Functionality) | Settings - Your Account | There's nothing to save, but the screen "Unsaved changes" still appears. | "Unsaved changes" should only appears when user have unsaved changes. |  | Not Done Yet
24 | iOS iPhone 14 Pro Max |  | Critical Bug | Ads | Ads are not showing for the free user | Ad should be there for the free users |  | Not Done Yet
25 | iOS iPhone 14 Pro Max |  | Critical Bug | Sign Up | While signing up, if the user navigates to the Date of Birth (DOB) screen and then clicks the "Cancel" button, the app crashes instead redirecting the user back to the Main screen. This disrupts the sign-up flow and may result in a poor user experience. | The user should be redirected to the Main screen when they click "Cancel" on the DOB screen. | https://drive.google.com/file/d/1vCh_KJ5-bKw5KGyvaBFCU6LbQnC9ajte/view?usp=drive_link | Done
26 | iOS iPhone 14 Pro Max |  | Critical Bug | Account | When a user signs up for the first time and lands in the app, certain tab layout icons incorrectly show as locked with an alert message stating,"This feature is available for premium only." However, after the user logs out and logs back in, the icon appears unlocked, even though the user has not purchased a premium subscription. This behavior creates confusion regarding feature access for non-premium users. | For non-premium users, the tab layout icon should remain consistently locked unless the user upgrades to premium. If the feature is free, it should appear unlocked immediately after sign-up without requiring a re-login. | https://drive.google.com/file/d/1j1TlouVN-d1G4LnR0UZdYwOkRvoWbgCL/view?usp=sharing | Done
27 | iOS iPhone 14 Pro Max | Khoa: A fix will be implemented when the app scale better K: There is currently a free 3 day trial with all new users. We will cancel the free 3 day trial this week / in the next patch. K: Free premium is gone | Critical Bug | Subscription | Huge Critical Bug - After purchasing a premium subscription with the account associated with QAmohan98@gmail.com on an iOS device (iPhone 14 Pro Max), logging out of this account and signing up or logging in with a different account incorrectly shows the new account as premium. This misrepresents subscription status and could lead to unintended access to premium features. | Each account should display its own subscription status independently. A non-subscribed account should not show as premium unless a subscription is purchased. | https://drive.google.com/file/d/1j1TlouVN-d1G4LnR0UZdYwOkRvoWbgCL/view?usp=sharing | Done
28 | iOS iPhone 14 Pro Max |  | Critical Bug | Add Partner | ` | The link should remain valid for a reasonable period (e.g., 24 hours) to allow the invitee time to join as a partner. | https://prnt.sc/Zi_Rf44uh0JK | Done
29 | Oppo Reno 8T | Khoa's | Bug (Functionality) | Sign Up | When I sign up mid way using Google, and then exit the app, The let's create "your profile" screen disappear, and I can't set my role and gender. |  |  | Done
30 | Oppo Reno 8T | Khoa's Dev: The timezone is set to 'NA' for users who previously had an old timezone that has now been removed from the app. The app now only supports UTC timezones, ranging from UTC -12:00 to UTC +14:00. If a user has a saved old timezone that is no longer in the database, it will show as 'NA'. Once the user selects and saves a new timezone, the correct timezone will be displayed. | Bug (Functionality) | Settings - Your Account | Timezone is NA, instead of the correct timezone. |  |  | Done
31 | iOS iPhone 13 Pro Max | K | Bug (Functionality) |  | Under Settings > Tab Layout > More Don't allow user to click on the word "More". Only the 4 slots are customisable. See this video here. When a user presses "More", nothing should happen. |  | video | Done
32 | iOS iPhone 13 Pro Max | K | Update |  | Remove 3 day free premium trial |  |  | Done
33 | iOS iPhone 13 Pro Max | K | UI/UX Bug |  | Stray "1" notification on iOS |  | stray_noti.jpg | Not Done Yet
34 | Realme X2 PRO |  | Improvement | Profile | Once a user uploads their profile picture, there is no option to remove it from their profile. | After uploading a profile picture, the user should have an option to remove or delete the profile picture from their profile if they choose. | https://drive.google.com/file/d/19fV41S_ZWwIEMO4FxP-8AQ_KkKcKBleE/view?usp=drive_link | Done
35 | Realme X2 PRO |  | Bug (Functionality) | Feedback | When providing feedback, if the user leaves all fields empty, the error message only highlights the Email field | If the user submits the feedback form without entering any data in any field, an error message should display for each required field, indicating that input is needed. | https://drive.google.com/file/d/1A8YSjGzRKh5cA2ReqSe2ZcPMk4sGBGwi/view?usp=drive_link | Done
36 | Realme X2 PRO |  | Bug (Functionality) | Feedback | When all fields except the Email field are left empty and the Send button is clicked, neither an error message nor a success message is displayed | If only the Email field is filled and other required fields are left empty, an error message should indicate which fields are missing input. Alternatively, if all required fields are completed correctly, a success message should confirm that the feedback was sent. | https://drive.google.com/file/d/1ACRpj8r2voHAAE5aGU43A9VArwOgoYIC/view?usp=drive_link | Done
37 | iPhone 14 pro Max |  | Critical Bug | Login with Apple | When a user logs in to the app using the "Sign in with Apple" feature, their name is displayed as "Null" in the Account section. | The user's name should be displayed correctly in the Account section. | https://drive.google.com/file/d/1MaZrbvIAJD7x3vfnu331g4fx-zr4Yv-9/view?usp=drive_link | Done
38 | Realme X2 PRO |  | Bug (Functionality) | Add a Partner | When using the "Switch User" feature, the application displays the user's online status instead of the Partner's role. | The application should display the Partner's role for the selected user. | https://drive.google.com/file/d/1A_zVoDske2Pfn35t6YLzdQe4YdmL-VZN/view?usp=sharing | Not Done Yet
39 | iPhone 14 pro Max |  | Bug (Functionality) | Add a Partner | When attempting to add a partner from the account QAmohan98@gmail.com, an undefined error appears, stating "expiration time is not defined." | Partner should be added successfully without any errors. | https://drive.google.com/file/d/1e_VThlA_rp49UomRZUm0nfLs00bJN156/view?usp=sharing | Done
40 | iOS iPhone 13 Pro Max | K | Critical Bug | Timezone offset. | I suspect the timezone in the whole app to be incorrectly offset. UTC+8 is offset by 30 mins. This is a repeated bug. please priortise and check 1) the system internal time 2) offsets are logging correctly | - | 1 2 3 4 | Done
41 | Figma | K Implement Action item 1 Update new Habit home display + Create / Edit Good / Bad Habit. | Update | Update to Habit module. Addition | Update Notes (Internal Only) New Habit home Change of create edit/habit to 1 pager Refinement of edit habit settings We are removing the words "Gain" and "Lose" in all screens, in in the assinging of rewards and punishments. Rewards 1 Point every time 1 reward_name every time 1 reward_name if done more than x times This update is pretty much putting the same buttons in different places. Addition of funtion: Doing a Habit "Once". There is no time limit. Once performed, task will auto delete. when assigning Rewards and Punishments, Setting of auto punishment to be "1 point" only. Conversely, setting of auto reward to be "1 point" only. | - | Figma | In Progress
42 | Realme X2 PRO |  | Bug (Functionality) | Add Journal | When an image is uploaded in Add Journal and the journal is saved, the image appears broken in the journal field. | When an image is uploaded in the Add Journal section and the journal is saved, the uploaded image should display correctly in the journal field without any errors or broken links. The image should retain its original quality and appear in the intended position within the journal entry. | https://drive.google.com/file/d/1AmKFei6HxaQ2labTyjlktGNJ8EMj30Ei/view?usp=sharing | Done
43 | Realme X2 PRO |  | Bug (Functionality) | Activity Timer | When the user sets a timer for 3-4 seconds and then moves the application to the background, upon reopening the application, the timer freezes. Even when clicking the Pause button, the timer does not resume. | When the user sets a timer for any duration and moves the application to the background, the timer should continue to run as expected. Upon reopening the application, the timer should display the correct time remaining. The Pause button should function correctly, allowing the user to pause and resume the timer as intended. | https://drive.google.com/file/d/1Am_kJgje-2js7GFR1pUDOaauNe_3V5_o/view?usp=drive_link | Done
44 | Realme X2 PRO |  | Critical Bug | Activity Timer | When user set timer for 3 -4 second & then move application in kind of background & when opens application agains & timer then freezes even when clicking on Pause button the timer doesn;t get resumed & when user clicks on + or - button then clicks on back button the whole screen turns black | When user set timer for 3 -4 second & then move application in kind of background & when opens application agains & the timer then freezes even when clicking on Pause button the timer doesn;t get resumed & when user clicks on + or - button then clicks on back button the whole screen turns black | https://drive.google.com/file/d/1ApZqzlKNE5Z6L7LLCIbDd_B4hrfRuY7j/view?usp=drive_link | Done
45 | Realme X2 PRO |  | Bug (Functionality) | Stopwatch | The Reset button remains clickable while the stopwatch timer is running. | The Reset button should only be clickable when the stopwatch is paused to prevent accidental resets during timing. | https://drive.google.com/file/d/1AygGPyza_fWQgzcRhNuk_1xCjTrpYA9Y/view?usp=drive_link | Done
46 | Realme X2 PRO |  | UI/UX Bug | Signature | In the signature field, if the user enters a lengthy signature, the signature overlaps with the delete icon. This overlap makes the delete icon difficult to access and impacts the usability of the signature field. | The signature should remain within the designated area, with no overlap on the delete icon. The delete icon should be easily visible and accessible, regardless of the signature length. | https://drive.google.com/file/d/1B6G6liERzjFzV_bc13GFCJIEhZwOvVrg/view?usp=drive_link | Done
47 | Realme X2 PRO |  | Improvement | Signature | Unnecessary Scrollbar on Edit Signature Page | The Edit Signature page should not display a scrollbar if the content fits within the screen area. | https://drive.google.com/file/d/1B7rf3souVt186ClMrDKpmkDtysVRHT0n/view?usp=drive_link | Done
48 | iOS iPhone 13 Pro Max | K | Critical Bug | Edit History - Input Tracker | When i toggle the date left and right, the date is not moving as intended. now left increases date by 1 month. right resets date to june 2023 | Left should reduce date. right should increases date | https://drive.google.com/file/d/1QDP5j6xmV2Q-XynzinMBdhHGWLpD_aBj/view?usp=drive_link | Done
49 | Realme X2 PRO |  | UI/UX Bug | Add Tracker | When adding new tracker with longer input in Number field than sessions field is kind of going out of box when tracker is created when sessions are being chosen from Counting of field | The user should be able to select sessions from the Counting field without visual distortion in the interface | https://drive.google.com/file/d/1BWsY1auwV0OSmDotlm1f_4V1p-lzNQ4Q/view?usp=drive_link | Done
50 | Realme X2 PRO | Dev: This is based on the Figma design and app functionality. Now, the upper checkboxes should either be removed or set to non-clickable. | Bug (Functionality) | Rewards | When text is entered into the Reward field, it is also displayed in the Punishment field, which should be independent. | The Reward and Punishment fields should be completely independent of each other. When text is entered in the Reward field, it should only appear in that field and should not affect or appear in the Punishment field. | https://drive.google.com/file/d/1BcJncPWXOtEA1O_MzruVb2xP2tLIkYE9/view?usp=sharing | Not Doing
51 | Realme X2 PRO |  | Bug (Functionality) | Stopwatch Presets | When a user enters a lengthy input for the stopwatch preset name and clicks the edit button, the entered title is cut off, displaying only half of the characters | When a user enters a lengthy name for the stopwatch preset, the full title should be displayed without cutting off characters | https://drive.google.com/file/d/1BfBu8N2932pceiKAXKKSlC8Iohh644Uj/view?usp=drive_link | Done
52 | Realme X2 PRO |  | Critical Bug | Stopwatch Log | When a lengthy input is entered as a preset name for the stopwatch, attempting to delete the corresponding log fails. | The log entry should be deleted successfully, regardless of the length of the preset name. | https://drive.google.com/file/d/1BfbwbrzmTs4nAGDIyUJ0MORuaIZhX4dC/view?usp=drive_link | Done

## Button (Discon.)
Scope | Test Case | Description | Pass/Fail/Pending-Android | Status | Result | Defect Description | Team comments | Media
Login/Registration | Start Birthday Selection Checkbox for i agree Cancel Continue Continue with Google Continue with Email Sign In Password hide/unhide Remember me checkbox Forgot Password Send Recovery Email | Test whether all the buttons are clickable or not. | Pass |  | All button works fine
Home Page | Invite Your Partner Pemium Pachage Logo Setting Habit Icon Reward Icon Journal Icon Rules | Test whether all the buttons are clickable or not. | Pass |  | All button works fine
Invite your Partner | Add Partner Add Switch Add Dominant Add Submissive Cancel Continue Copy Share Back Button <--- | Test whether all the buttons are clickable or not. | Pass |  | All button works fine
Habit | Good Habit Band Habit Add Habit Button ➕ Checkbox Good Habit Checkbox Bad Habit Cross Button ✖️ Continue Checkbox Daily Weekly Monthly Checkbox At Most At Least Increasing Sign + Decreasing Sign - Time scrolling Checkbox Upon Completion of Habit Every time a habit is done When a habit is missed Delete Icon Edit Icon Save | Test whether all the buttons are clickable or not. | Pass |  | All button works fine
Habit | In the Giant Point checkbox, we can only select it, but we are unable to unselect it once selected. | checkbox should be able to both select and unselect. Reprodure step : >Create Habit > Go to last page of creation .Before save >Two option Reward/ Punishment > Click edit Icon >Click Gain Point > Select checkbox then try unselect | Fail
Reward | Rewards Punishments Log Icon Increasing Sign + Decreasing Sign - Checkbox Reward Checkbox Punisment |  | Pass
Pass
Pass
Pass

## Design Checklist
Design task list
No. | Description | Priority | Status
1 | Implement share function - when users take a screenshot, popup menu of share options | Medium | Start
2 | Gender toggle in the settings page | Low | Pending
3 | Colour customisiation design | Low | On going
4 | Add on to the tab customisation module, To de-select / hide modules that users don’t want to use | Low | Start
5 | Mood tracker calendar | Suggestion | skip
6 | Add another tutorial about the add partner: Since the switch thing, set roles, and connected status instead of online | Low | Pending
7 | Update top nav bar for Switch usres - Online becomes Dom/Sub | Low | Pending
8 | discuss about "Days completed" discuss about the creation date for habits/R&Ps | Low | KIV
9 | Unlocked Premium screen: Thank you for getting Binded with us. | Low | Pending
10 | Website Redesign | Low | On going
11 | Spec out all Free version notifications | Low | Pending
12 | Notification managent module | Low | KIV
13 | Dual time display for Dom/Sub to allow users to choose which timezone they wish to view the log | Low | Pending
14 | Redesign create/edit R&P flow to match Habits | Low | Pending
15 | Expand Notes past limit of 4 | Low | Pending
16 | Refresh Tutorials | Low | Pending
17 | Refresh App Store and Play Store app images | Low | Sidny - In Progress
18 | Locked Note functionality | Suggestion | Pending
task list archive
No. | Description | Date Archived | Status
1 | Check permissions for modules to check that both roles can do all functions. Permissions will govern who can do what. | 2024-10-16 | Done
2 | Sub-sub pairs. We should have a prompt to allow 1 user to switch to dominant (discussed, dropdown menu and popup to be implemented) | 2024-10-16 | Done
3 | Combined UI for 1 Dom managing multiple subs , dropdown menu in top bar to be implemented ONLY FOR MULTIPLE USERS | 2024-10-16 | Done
4 | Keep personal space, note last viewed partner (for multiple). for 1-1 partners. auto toggle this partner. + popup to help users who think their solo habits are gone) | 2024-10-16 | Done
5 | Make toggle more obvious, keep delte button ,add confirmation to delete partner) | 2024-10-16 | Done
6 | Combined UI for 1 Dom managing multiple subs , dropdown menu in top bar to be implemented ONLY FOR MULTIPLE USERS | 2024-10-16 | Done
7 | Keep personal space, note last viewed partner (for multiple). for 1-1 partners. auto toggle this partner. + popup to help users who think their solo habits are gone) | 2024-10-16 | Done
8 | Make toggle more obvious, keep delte button ,add confirmation to delete partner) | 2024-10-16 | Done
9 | if you pause a habit, it changes nothing. Response: your interpretation is correct. if the habit is paused, the habit no longer issues rewards and punishments (it does nothing as there is no habit due) Edited response: it should be clear for users when a habit is paused. | 2024-10-16 | Done
10 | Quick permission menu; and make permission enabled by default for both dom and sub | 2024-10-16 | Done
11 | Check notifications on IOS and Android | 2024-10-16 | Done
12 | Design buy and complete button | 2024-10-16 | Done
13 | New changelog 1.4 | 2024-10-16 | Done
14 | Price updates, promos and implementations | 2024-10-16 | Done
15 | Quick partner toggle button in the nav bar | 2024-10-16 | Done
16 | Testing of Android - iOS cross platform functionality | 2024-10-16 | Done
17 | Sub-sub pairs. We should have a prompt to allow 1 user to switch to dominant (discussed, dropdown menu and popup to be implemented) K: Confirm with Jaya if there will be an "Add switch button" or not, check functionality, and update Figma accordingly | 2024-10-24 | Done
18 | Redesign the permission menu | 2024-10-24 | Done
19 | Design ads in habits [DELETED] | 2024-10-24 | Done
20 | Ads in Binded+ | 2024-10-24 | Done
21 | New settings page K: If we intend to proceed with this first, and the "Colour Palette" module is not ready, just put "Coming Soon" to replace the word "Colour Palette" | 2024-10-24 | Done
22 | "Please ensure activity timer module works as intended (functionality, log, flow, presets, running in background etc) Note: Activity Timer modules should stay running even through the app is closed/inactive. the timer has to run 24/7 regardless if the phone is on or off. " | 2024-11-03 | Done
23 | New changelog 1.5 | 2024-11-03 | Done
24 | New navbar and Icons | 2024-11-03 | Done
25 | Update UAT + bug sweep | 2024-11-03 | Done
26 | Check Logs | 2024-11-03 | Done
27 | "Let’s add a text under weekly and monthly habit setup. Rewards and punishments will be issued at the end of the period for at least and at most. K: Create Habit pending" | 2024-11-14 | Done
28 | End Free Premium Promo in 2 patches (No more free premium on week of 4 Nov onwards) | 2024-11-14 | Done
29 | Implement smart save/continue button | 2024-11-14 | Done

## creds (hidden)
email | password
QAtest@yopmail.com | TESTQA
QAmohan@yopmail.com | QAmohan

## GENERAL
General Information:
Objective: To validate the module and its features against the defined requirements.
Prerequisites: Ensure the app is installed and the tester is logged in with the necessary permissions.
Test Data: Provide any specific data or configurations needed to test the module.
Website | www.binded.app
Figma | https://www.figma.com/design/nHj7o8IYKhcS2caFLyY2Hl/Binded-%7C-BDSM-Lifestyle-App?node-id=6309-1046&node-type=canvas&t=EyPOy9WQXadekvuS-0
Checklist:
Test Case | Pass/Fail | Comments/Issues
1.1 Verify that the user can access the [feature]. |  | Ensure the feature is visible and accessible.
1.2 Test the [feature] functionality under normal conditions. |  | Confirm the feature works as expected under typical use.
1.3 Test [feature] when user inputs edge cases. |  | Test how the feature behaves with edge case inputs.
1.4 Verify error messages when [feature] fails. |  | Check if appropriate error messages are shown.
1.5 Ensure data entered in [feature] is saved correctly. |  | Confirm that input data persists.

## Performance
Scope | Test Case | Description | Pass/Fail/Pending-Android | Status | Team comments | Defect Description | Expected result | Media
Memory Leakage | Measure how much memory our app consumes. | After logging in, our app consumes approximately 299KB of data and caches around 250KB. When adding a new note, it consumes an average of 12KB per note. | Pass
Interrupt | Incoming and outgoing Sms Incoming and outgoing Calls Incoming Notifications In Charging mode low battery power | We're testing how our app performs in situations such as incoming and outgoing SMS and calls, incoming notifications, charging mode, and low battery power. This allows us to assess the app's behavior under various conditions to ensure a smooth user experience. | Pass
Installation | Verify Installation | Verify that the installation process is smooth and does not take long. Verify that the installation is successful through enterprise app store. | Pass
Unistallation | Verify Unistallation | Verify that all the application related files are removed successfully after uninstallation. | Pass
App Launch time | Launch Time | Measure time taken to open the app. It's taken less than 2 second. | Pass
Battery Usage | Test the app's impact on battery consumption | Analyze the app's effect on battery consumption. Screen time 1 hr 40min Background: lessthan a min Battery usage 6%/100% | Pass
App Permissions | Verify app permission | Check app permissions for deavice features.Verify permissions are requested only when necessary. | Pass

## 1. LOG IN , REGISTER , PARTNERS
Checklist:
Scope | Test Case | Last Date Logged | Description | Pass/Fail/Pending-Android | Status | Team comments | Defect Description | Expected result | Media
App | Verify the app logo Verify that the installation is successful through enterprise app store. Verify that after seaching our apps on app store it showing right app or not. Verify that app contain correct name or Title Verify the app launching time |  |  | Pass
Log in | Verify the page after open the app that match with figma design or not. Check start button clickable or not. |  |  | Pass
Log in | Check the waring message . It contain same content or not or is there any spelling isuue. Verify the birthday calender input field and selecting pop up. Verify Checkbox workable or not like select/unselect. Verify "Cancel" and "Continue button" clickable or not. Verifly without selecting any DOB click continue gives us warning message or not Verify It accept only 18+ ages or not |  |  | Pass
Log in | App should be adjust to fit any screen size. But in larger displays require little scrolling. It happesn on warning page. UI/UX issue |  |  | Fail | Minor |  | "The app should adjust to fit any screen size, but on larger displays, minimal scrolling is required. This occurs on the warning page and is a UI/UX issue." | The app should adjust to fit any screen size | Image
Log in | Verify Continue with Google ,Continue with Email , Sign in Button are clickable or not. |  |  | Pass
Log in | >Verify input fields taking input or not >Try to login using invalid email and password and get some error message >Try to login using invalid email and valid password and get some error message >Try to login using valid registerd credentials and succesfully go into next page. >Try to login using unregistered credentials and get error message |  |  | Pass
Log in | >Verify password hide/unhide icon works or not. >Verify Remember me checkbox works or not. >Verify remember me functionality works or not. >Check forgot password button works or not. >Try to recover password input invalid email and get a error message >Try to recover password using unregisterd email and get error message. >Check "Send Recover email" Button workable or not. > After clicking Send recovery Button verify we are getting an OTP or not. >Try to recover using invalid OTP and get error message. >Check Cancel and Submit button workable or not. >Check recover password functionality workable or not |  |  | Pass
Register | As Figma design For andriod Continue in with Google, Continue in with Email Sign in Button Clickable or not |  |  | Pass
Register | >Ensure continue with google functionality works or not >In continue with email check all input field are working or not. Name box Email box password box Confirm password box >Check hide/unhide icon workable or not. >Try to sign up without filling any data and get a error message. >Try to signup with envalid email and get error message . >Try to sign up without filling name field and get a error. >Try to sign up filling Confirm password field that not match with Password field.And get error message. >Try to sign up using too short password less than 6 digit and get a error message. >Check Continue button workable or not. >Check Cross button ✖️ workable or not. >Try to sign up with correct information and Succesfull |  |  | Pass
Register | >Sign up with long character acceptable .But I suggest a 20 character password limit. >There is no requirement in password field like use one symbol, Numeric character, Alphabet |  | Improvment | Pass | Done
Register | >Profile Create >Check timezone dropdown workable or not >Check role checkbox workable or not >Check gender checkbox workable or not >Verify back button Verify Continue Button >Verify cross ✖️ button |  |  | Pass
Register | In profile creation the search field of timezone dropdown not work properly | 2024-11-11 | > After registration page go to profile creation page >Click on timezone seach field >Input a valid timezone that available | Pass | Done |  | When we search any timezone using seach field Like UTC -04:00. It shows nothing to see here...yet.Although this timezone is available. | It should be show available timezone | Image
Register | OTP Verification Check it send otp in our email. Try to submit invalid otp and get a error. Check Resend OTP button work or not Check verify Email Button |  |  | Pass
Register | Set Passcode Input less than 4 digit pin and submit ,Get a error message Verify Save button |  |  | Pass
HomePage | Check No Partner Button Check Premium submisson Icon Check Setting Icon Check Habit Icon Check Reward Icon Check Journal Icon Check Rules Icon |  |  | Pass
Partner | Case 1 : No Partner Added Check Setting Check Back Button Check Add Partner button Check Content | 2024-11-24 | UI/Ux Issue | Pass | Done |  | In the Figma design, the content shows "Add a partner by tapping the button below," but in our app, it currently displays "Nothing to see here... yet." | It should show "Add a partner by tapping the button below," this as a content | Image
Partner | Case 2: 1 Partner Added Setting Check Back Button Check Partner Button Check Add Patner Button Check remove partner Funtion+ Popup Cancel,Remove Button Check Turn on/off Button for partner |  |  | Pass
Partner | Case 3: 2 or more partner addded Setting check Partner Button Check Back Button Switch Partner Partner 1 Check remove partner Funtion+ Popup Cancel,Remove Button Partner 2 Check remove partner Funtion+ Popup Cancel,Remove Button Add partner |  |  | Pass
Partner | Add Patner Check Content Check add switch Button Check add Dominant Button Check add submissive Button |  |  | Pass
Partner | Warning message for Same role | 2024-11-11 | Add same role partner it do not give any warning messsage | Fail | Major | K: Khoa please look into this | The warning message only appears when I try to switch roles, not when adding a partner with the same role. | It should be give us warning when we add same role partner | Video
Partner | Popup Each section Sub: Check, Continue Button Dom: Check, Continue Button Sub:Check, Continue Button Check Copy and share Check Funtionality of Share |  |  | Pass
Partner | Invitation window Check confirm verify Check decline Button |  |  | Pass
Partner | Content Improvement | 2024-11-11 | Improvment | Pass | Improvement |  | When I send an invitation with a specific role set, the person who accepts it should not be able to change their role. Therefore, the invitation message should read: "[Name] has invited you to be their partner as a Dominant or Submissive. |  | Image
App icon | On iOS, there is a "1" notification. It does not go beyond 1, regardless of how many notifications are actually received. We also cannot get rid of the "1" notifcation. | 2024-11-11 | UIUX | Fail | Major | K: retest. | random "1" notification on iOS | Notifications should display how many notifications are received | stray_noti.jpg
Advertrisements | No ads appearing for free users. | 2024-11-11 | functionality | Pass | Done |  | No ads appearing for free users | ads should appear once every 4 mins of use
Timezone | 30 mins offset at UTC+8 60 mins offset at UTC+7 | 2024-11-11 |  | Pass | Done |  | timezone offset in log | display the correct time in the log | 1 2 3 4

## 2. SETTINGS
Checklist:
Scope | Test Case | Date Logged | Description | Pass/Fail/Pending-Android | Status | Team comments | Defect Description | Expected result | Media
Main Setting | Check The Button are clickable or not: Account Account Edit Icon Back Partner Permissions Premium Passcode Tab Layout Colour Palette FAQ About Feedback |  |  | Pass
Main Setting | FAQ Button displays as "FAQ" But in Figma design it shows as "FAQs" | 2024-11-24 | Minor UI/IX issue | Pass | Done |  |  |  | Image
Main Setting | Account ,Account Edit Icon do same thing. Account should be read only mood. Account Edit Icon should be for editing or update information | 2024-12-11 | Improvment | Pass | Done |  |  |  | Video
Account | Upload profile picture and remove picture Name field Editable or not Old Password field New password field Verify password change funtionality Check Hide/Unhide Icon Timezone dropdown Save Button Log out Button Delete Account Button + Popup ( Yes, No) Change Button Unsaved Changes Popoup + Leave without saving , Save |  |  | Pass
Permssions | For Reqular Click permission and open popup warning |  |  | Pass
Pemissions | Habits Dropdown Button Checkboxs Enable/Disable all Complete Create Edit Delete Pause Change History Save Button |  |  | Pass
Pemissions | Rewards Dropdown Button Checkboxs Enable/Disable all Add/Remove Points Create Edit Delete Buy Complete Manually Adjust Save Button |  |  | Pass
Pemissions | Punishments Dropdown Button Checkboxs Enable/Disable all Create Edit Delete Complete Manually Adjust Save Button |  |  | Pass
Pemissions | Journal Dropdown Button Checkboxs Enable/Disable all Create Edit Delete Save |  |  | Pass
Pemissions | Rules Dropdown Button Checkboxs Enable/Disable all Edit Sign Save |  |  | Pass
Premium | Premium Button Subscription Confirmation Popup (Yes ,No) Back Button |  |  | Pass
Passcode | Not Asking previous Passcode Passcode Functionality All number Clickable Save Button Back Button |  |  | Fail | Done |  | If the system doesn’t prompt for the previous passcode before allowing a change, it could pose a security risk. For instance, if someone else gains access to the app, they could change the passcode and close it, leaving the original user locked out of their own data. | Old/Previous Passcode> New Passcode>Confirm Passcode
Tab Layout | Warning message for free User |  |  | Pass
Colour Palette | Coming Soon Back Button |  |  | Pass
FAQ | Content available Back Button |  |  | Pass
About | Term Of Use + Dropdown icon+ Forward Button Privacy Policy + Dropdown icon+ Forward Button Back Button |  |  | Pass
Feedback | Name Field Email Field Title Field Feedback Send Button |  |  | Pass
Feedback | Set limitation for Feedback Description Like 300 words | 2024-12-11 | Improvment | Pass | Done |  |  |  | Image
Version Check | Content available Read More Read Less Ok Button |  |  | Pass
Social Media | X Icon + Popup Cancel, Continue Instagram Icon + Popup Cancel, Continue Reddit Icon +Popup Cancel, Continue Website Icon+Popup Cancel, Continue |  |  | Pass

## 3. HABITS
Checklist:
Scope | Test Case | Description | Pass/Fail/Pending-Android | Status | Result | Log Date | Team comments | Media
Create Habit | Create Habit 1 Check box Good Habit & Bad Habit Name of Habit Habit Description | Pending New UI
Add Habit-1 | Name of Habit Habit Description Notification Continue Button Cross Button Back Button |  | Pass
Add Habit-2 | Habit Tracked Checkbox Daily Weekly Monthly At Most At Least Increasing Icon + Decreasing Icon - Input Point Manuallly Continue |  | Pass
Add Habit-3 | Habit Due time Notification Checkbox Upon Completion of Habit Every time a Habit is done When a Habit is missed Continue |  | Pass
Add Habit-4 | Add Reward and Punishment for Habit Remove Reward Edit Reward Checkbox Every time If done more then If done less than Time set field Gain Point Dropdown Gain Point Checkbox Ok Button Cancel Button |  | Pass
Add Habit-4 | Add Reward and Punishment for Habit Remove Punishment Edit Punishment Checkbox Every time If done more then If done less than Time set field Lose Point Dropdown Lose Point checkbox Ok Button Cancel Button |  | Pass
Add Habit-4 | UI/Ux Issue on Edit Punishments Page Page. It shows "Edit Punish..." | In the Habit creation process, navigate to the "Edit Punishments" page and check the headline. It displays as "Update Punis..." | Pass | Minor | Expected Result should be "Edit Punishments" | 2024-11-24 | K: now visible. Acceptable | Image
Edit Habit | Back Button Cross Button Paused/Un-paused Delete Habit + Yes ,No Popup Edit Habit Name of Habit field Habit description Continue Button Back Button Log Functionality Edit History |  | Pass
Notification | Habit Minus Sign | When we click the plus sign, it triggers a notification, but clicking the minus sign does not generate any notification. | Fail |  | when the minus sign is clicked, a notification should be triggered, indicating the removal or deduction. | 2024-11-18 | K: Khoa please look into this
Default Reward and Punishment for Habits |  | For Good habits, please set the default reward to "1 point". No default punishment. For Bad habits, please set the default Punishment to "1 point". No default reward. | Fail | Minor |  | 24/11/24
Binded+
Add Habit | Habit description Field | The habit description supports up to 200 words, but it currently displays in a single line, which makes editing difficult for users. Since we aim to create a user-friendly platform, displaying the description in multiple lines would enhance usability. This issue wasn't present in our previous version. Additionally, the placeholder text in the description field currently displays as "Enter description Name," but it should simply say "Enter description" | Fail |  | The habit description should display in multiple lines by default, with the option to expand for longer content. The placeholder text should read "Enter description" instead of "Enter description Name" for. | 2024-11-24 | K: updated instructions | Image
Add Habit | Habit Track | The graphical interface does not align with the Figma design. The app's interface should adapt to fit any display size. However, in the Habit Tracker section, the Monthly button is slightly cut off, requiring a slight left scroll to view it fully. This needs to be adjusted to ensure a seamless user experience. | Fail |  | The app's interface should fully align with the Figma design. All buttons, including the Monthly button in the Habit Tracker section, should be fully visible without requiring any scrolling, regardless of the display size. | 2024-11-21 |  | Image

## 4.REWARDS & PUNISHMENTS
Scope | Test Case | Description | Pass/Fail/Pending-Android | Status | Result | Log Date | Team comments | Media
Point Box | Increasing Icon + Decreasing Icon - Input Point Manuallly |  | Pass
Add Reward Button ➕ | Reward CheckBox Name Field Description Point Cost Increasing Icon + Decreasing Icon - Input Point Manuallly Add Button Back Button Cross Button |  | Pass
Rewards | Buy Reward Claim Reward Remove Reward+ Yes ,No Popup Update Reward Name Field Description field Point Cost Increasing Icon + Decreasing Icon - Input Point Manuallly Back Button Cross Button Update Button |  | Pass
Rewards | UI/Ux Issue on update reward Page. It shows "Update Rewa.." | Go to update reward page then check Headline. It shows "Update Rewa..." | Fail | Done | Expected Result should be "Update Rewads" | 2024-12-11 |  | Image
"Add Punishments Button ➕" | Punishment CheckBox Name Field Description Field Add Button Back Button Cross Button |  | Pass
Punishments | UI/Ux Issue on Add Punishments Page Page. It shows "Add Punishm..." | "Go to Add Punishments page then check Headline. It shows ""Add Punishm..." | Pass | Done | Expected Result should be "Add Punishments" | 2024-11-24 |  | Image
Punishments | Claim Remove Punishments+ Yes ,No Popup Edit Punishments Increasing Icon + Decreasing Icon - Input Point Manuallly Name Field Description Update Button Cross Button Back Button |  | Pass
Punishments | UI/Ux Issue on Updates Punishments Page Page. It shows "Update Punis..." | "Go to Update Punishments page then check Headline. It shows ""Update Punis..." | Pass | Done | Expected Result should be "Update Punishments" | 2024-11-24 |  | Image
Log | Verify Log Functionality |  | Pass
Log | Log Timestamp | The app doesn’t change based on the timezone; it detects the timezone automatically, so if I change my timezone, it continues working as before. If we create a log entry the timestamp always capture local time | Pass | Done | The result should follow the current timezone set by the user. | 14/11/2024 |  | Video
Notification | Add Reward Notification Add Punishment Notification Increment reward point notification Decrement reward point notification Update reward notification Update punishment notification |  | Pass
Notification | Remove Reward Notification Remove Punishment Notification | When a reward or punishment is added, my partner receives a notification. However, when a reward or punishment is removed, no notification is sent to my partner. | Fail |  | Receive a notification when a reward or punishment is removed. | 14/11/2024
Notification | Buy reward notification Complete rewad notification | The notifications for "Buy reward" and "Complete reward" are giving the same message. On my phone, it displays as "Your submissive has claimed Snack," while on my partner's phone, it says "Enjoy your snack." | Fail |  |  | 14/11/2024 | K: Khoa please implement new notifications | Video

## 5.JOURNAL
Checklist:
Scope | Test Case | Last Date Logged | Description | Pass/Fail/Pending-Android | Status | Team comments | Defect Description | Expected result | Media
Add journal | Title Field Date + Calender Popup + Ok, Cancel Tag Field Description Save Button Back Button Cross Button |  | Pass | Pass
Journal Description | Undo Redo Font Size Bold Italic Underline Font Color Background Color Align left Center Right Justify win width Checked list Save Button Back Button |  |  | Pass
Journal Description | Numbered List Bullet List | 2024-11-24 | UI/UX Issue | Pass | Done |  | The numbered and bullet lists in the description aren’t visible clearly because their default color matches the background color. This makes them difficult to read. | The numbered and bullet lists in the description should visible clearly | Image
Journal Home | Delete Journal + Yes, No Popup Update Journal Update Button |  |  | Pass
Journal | Update Journal | 2024-11-24 | Ui/UX Issue | Pass | Done |  | On the "Update Journals" page, check the headline. It displays as "Update Jour..." instead of the full title. | "Expected Result should be ""Update Journals""" | Image
Journal Description | Checked list | 2024-11-24 | Ui/UX Issue | Pass | Done |  | The text in the description field is usually visible in white, but when we click on the checklist icon and start typing, the text becomes invisible. | TheChecked List content in the description should visible clearly | Video
Notification | Remove Journal Notification | 15/11/2024 | Functional issue | Fail | Done |  | When a Journal is added, my partner receives a notification. However, when a Journal is removed, no notification is sent to my partner. | Receive a notification when a journal is removed.
Journal Description | Numbered List Bullet List | 2024-11-24 | UI/UX Issue | Pass | Done |  | Numbered and bullet lists in the description are clearly visible while editing, but after saving, they are not Visible as their default color matches the background color. | Numbered and bullet lists should retain a contrasting color after saving to ensure they are clearly visible | Video

## 6.RULES
Checklist:
Scope | Test Case | Last Date Logged | Description | Pass/Fail/Pending-Android | Status | Team comments | Defect Description | Expected result | Media
Rules | Edit rule Button "Undo Redo Font Size Bold Italic Underline Font Color Background Color Align left Center Right Justify win width Checked list Save Button Back Button" |  |  | Pass
Edit Rules | Numbered List Bullet List | 2024-11-24 | UI/UX Issue | Pass | Done |  | The numbered and bullet lists in the Rule description aren’t visible clearly because their default color matches the background color. This makes them difficult to read. | The numbered and bullet lists in the description should visible clearly | Image
Edit Rules | Checked list | 2024-11-24 | Ui/UX Issue | Pass | Done |  | The text in the rule description field is usually visible in white, but when we click on the checklist icon and start typing, the text becomes invisible. | TheChecked List content in the description should visible clearly | Video
Signature | Add Signature Delete Signature Signature Field Cross Button Save Button Back Button |  |  | Pass
Signature | Update signature notification | 2024-11-18 | Functional | Fail | Done |  | When we update the rules, the notification correctly states "Rules updated," but when we update the signature, it also incorrectly notifies "Rules updated." | Expected result should be "Signature updated"
Edit Rules | Numbered List Bullet List | 2024-11-24 | UI/UX Issue | Pass |  |  | Numbered and bullet lists in the description are clearly visible while editing, but after saving, they are not Visible as their default color matches the background color. | Numbered and bullet lists should retain a contrasting color after saving to ensure they are clearly visible | Video

## 7.NOTES
Checklist:
Scope | Test Case | Last Date Logged | Description | Pass/Fail/Pending-Android | Status | Team comments | Defect Description | Expected result | Media
Notes | Edit Notes Title Edit note Title input field Popup > Cancel+Submit Note title Dropdown |  |  | Pass
Notes | Undo Redo Font Size Bold Italic Underline Font Color Background Color Align left Center Right Justify win width "Numbered List Bullet List" Checked list Save Button Back Button |  |  | Pass
Notes | Switch Notes Notification |  |  | Pass

## 8.ACTIVITY TIMER
Checklist:
Scope | Test Case | Last Date Logged | Description | Pass/Fail/Pending-Android | Status | Team comments | Defect Description | Expected result | Media
Stopwatch | Play Button | 2014-11-23 | The play/pause button has a slight delay in starting the timer. | Fail |  | Dev: This is due to data is loading from socket backend |  | The play/pause button should respond immediately, starting or pausing the timer without any delay.
| Reset Button Log View Details Choose day Delete Log Done Button Close Button Back Button |  |  | Pass
| Set Preset Delete Preset Edit Preset+popup Submit,Cancel Preset Functionality |  |  | Pass
| Timer Calculation | 2014-11-23 | After resetting the timer for any preset, if the same preset is selected again, the timer does not reset and continues from the previous time. For example, if the timer is reset after 7 seconds, it will start again from 7 seconds instead of resetting. K: When stopwatch is opened, it tends to start from random timings like 32s or 41s instead of 0s like intended. Note that this timer is supposed to be logging time spent doing an activity. Having the timer start from random timings is counter intuitive. Timer should always start from 0. | Fail | Done | K: From no preset, when i select a preset, it starts at a random time and not from 0. |  | After resetting the timer for any preset, selecting the same preset again should reset the timer to its initial value | Video https://drive.google.com/file/d/1BCLWNyG2i9Bc2Z6aBLigsPWJM7_ote1C/view?usp=drive_link
| Activity timer module | 2014-11-23 | After using Activity timer module a few times, switching to another module, and then clicking the "More" icon again, the options do not appear. To resolve this, we have to close the app and reopen it to access the Activity Timer module again. | Fail | Done |  |  | The "More" icon should always display options without requiring the app to be closed and reopened, even after switching modules. | Video
| Activity timer module | 2014-11-23 | If we use this module a few times, such as changing presets 3 or 4 times and clicking other options like Log or Notification, it unexpectedly redirects to the Habit module. | Fail | Done | K: this causes bug above in line number 7 to occur. |  | After changing presets multiple times and clicking on other options like Log or Notifications, the app should not redirect to the Habit module unexpectedly. It should stay on the current module. | Video https://drive.google.com/file/d/18_CysXatXw3vGQoEj4B8XoaHfnelCIH6/view?usp=drive_link
| Notification Start Stopwatch Stop Stopwatch | 2014-11-23 |  | Pass
| Running in background | 2024-11-24 | Please note the terminology This module is called "Activity Timer" - consisting of 2 functions - a stopwatch and a timer. Only 1 instance of an activity timer can be running at any 1 time. Meaning: Either 1 stopwatch or 1 activity timer can run at any 1 time. If preset 1 stopwatch is running, user will not be able to start preset 2 stopwatch, or start a timer. Only 1 instance of an activity should be running in the background at any 1 time | Fail | Done |  |  | If stopwatch preset 1 is running. dont allow users to start stopwatch preset 2 or timer. If stopwatch preset 1 is runnning, only stopwatch preset 1 should be running in background. Do not allow user to start other presets or start timer | https://drive.google.com/file/d/1VrVVTIhMOa-Ii21wm7ESdWgqMkYmMAwa/view?usp=drive_link
| Stopwatch preset random start | 2024-11-24 | Stopwatch has no preset selected. Context: I have 2 saved presets. When there is no preset selected, I press stopwatch start. Preset is toggled and starts from a random timing | Fail | Major |  |  | When there is no preset selected, and i click stopwatch start, presets should not auto toggle. When no preset selected, stopwatch should record time with No preset. | https://drive.google.com/file/d/1vg_X86I1OzpbLPzhtIDBCcCEysKiS91D/view?usp=drive_link
| Preset Error | 2024-11-24 | If all presets are removed and the stopwatch is started, it still displays the name of a previously deleted preset. | Fail | Done |  |  | When all presets are removed and the stopwatch is started, it should display a blank or default name instead of showing the name of a previously removed preset. | Video
| Reset and Log Time function | 2024-11-24 | When i click into a saved preset, 1) issue 1: random start time above 2) when i press reset, nothing happens 3) when i press save, the time is still there | Fail | Major |  |  | 1) as mentioned above 2) when i press reset, time should reset to 0 3) when i press save, time should enter into log, and then stopwatch should reset to 0 | https://drive.google.com/file/d/1QgGrui4YNVcfazGmSQ60ndcWMIf4Fr5-/view?usp=drive_link
| Log understanding | 2024-11-24 | Lets say the activity is “walking” Every time I walk, I turn on the stop watch. When I am done, I press pause and press save. Each time I save = 1 session Let’s say I have 5 sessions Session 1: 1 min 2: 5 mins 3: 10 mins 4: 15 min 5: 4 mins Total time : 35 mins Average time: 35 / 5 sessions = 7 mins | Fail | Done | Press reset = time should not save Press log = time should save one time, and then reset stopwatch to 0
Timer | Play Button Log Button Days Input field Timer Scrolling Hours Mins Sec |  |  | Pass
| Log understanding | 2024-11-24 | Timer counts backwards from time set. For example: my partner allows me to eat a cookie in 1 day 10 mins I start a timer from 1 day 10 mins When timer is up, alarm rings. | Fail | Done |  |  | For timer, only completed timers go into log Stopping a timer midway = do not save into log | https://drive.google.com/file/d/1K7zb7byDzfe5MYZFvhfquYuxX0OGsnrc/view?usp=drive_link
| Timer end, no alarm ring | 2024-11-24 | When timer runs out, alarm does not ring Please use attached audio. Audio should cancel once the users clicks on the screen | Fail | Done |  |  | alarm should sound when timer reaches 0 | https://drive.google.com/file/d/1HGIctxzmjjw6ucjqUXhC4juu8gdrGAKE/view?usp=drive_link https://drive.google.com/file/d/1EC4TSWyVJhnKKO5MeTzCJUPbdKN2J6NX/view?usp=drive_link
| Timer log | 2024-11-24 | When the timer ends, it logs as two sessions, even though only one session was completed | Fail | Major | K: log seems to be double logging completed timers. only 1 log entry per completed timer Also, total time and average time is not logging correctly. For understanding 1 completed session = 1 saved log. Lets say Session 1: 1 min 2: 2 min 3: 2 min 4: 5 min 5: 15 min Total time: 25 mins Average time: 5 mins If a timer is stopped midway, there should be no saved log. |  | When the timer ends, it should log only one session, accurately reflecting the completed activity. | Video
| Running in background | 2024-11-24 | only 1 activity timer runnning at any 1 time | Fail | Done |  |  |  | same as above
| Not Running in background | 2024-11-24 | We set a timer and stopped it, then switched to another app on the phone for a few seconds. Upon returning to our app, the timer preset was removed. When we reselected the preset, it appeared as "finished." | Fail | Major |  |  | If a timer is set and stopped, then the user navigates to another app for a few seconds before returning, the timer preset should remain intact and not be removed. Upon reselecting the preset, it should resume or restart as expected, rather than showing it as "finished." | Video
| Timer log Notification | 2024-11-24 | When accessing the timer log and selecting "Total" or "Monthly," an unexpected and irrelevant notification appears, may be originating from the backend. | Fail | Done |  |  | When viewing the timer log and selecting "Total" or "Monthly," the app should display accurate and user-friendly notifications or content. | Video
| Timer UI/UX | 2024-11-24 | When starting the timer without a preset, it displays "No availab..." but it should display "No Available Preset." | Fail | Done |  |  | When starting the timer without a preset, the message should display as "No Available Preset" in full, without any truncation. | Image
| Timer Log | 2024-11-24 | If we set the timer for 6 seconds, the log section should display the duration as 6 seconds. However, it is currently showing 5 seconds. | Fail | Done |  |  | If the timer is set for 6 seconds, the log section should display the exact duration as 6 seconds, ensuring accurate tracking. | Video
| Timer Log | 2024-11-24 | In the timer log, the alignment of Date, Time, and Duration is inconsistent, appearing slightly misaligned when multiple logs are saved. | Fail | Done |  |  | The Date, Time, and Duration in the timer log should be properly aligned in a straight line for all entries, regardless of the number of logs saved. | Image
| Timer Notification | 2024-11-24 | Although this is a minor issue, it doesn't look good. The "T" in the notifications for "start timer" and "stop timer" is in lowercase. | Fail | Done |  |  | The notifications for "Start Timer" and "Stop Timer" should have the "T" capitalized to maintain consistency and proper formatting. | Image

## 9.INPUT TRACKER
Checklist:
Scope | Test Case | Last Date Logged | Description | Pass/Fail/Pending-Android | Status | Team comments | Defect Description | Expected result | Media
Input tracker | Add session (Add media) | 24/11/2024 | When adding media, i am only allowed to add files. I also want to be able to add images | Fail | Major | Dev: When we open files to upload on iOS, we first need to add camera images to the files, and only then can we select those images from the files. If we want to open images directly, the "Images" section must be opened for selection. To resolve this issue, we can create a dialog box that appears after clicking the "Add" button. The dialog box will have three options: Image, Video, and Audio. When the user selects Image, the gallery will open directly to allow image selection. Similarly, selecting Video or Audio will open the respective sections for selection. Should we implement this solution? K: yes |  |  | https://drive.google.com/file/d/1TIYi-vtScDVo0bQ-_XSyg8PGuflOstKF/view?usp=drive_link https://drive.google.com/file/d/1B51XDKoQLU55gVLoVj1m90rB6IUfGvO4/view?usp=drive_link
| Add session (Custom tracker) | 24/11/2024 | For alphanumerical custom trackers 1) remove ability to reset numerical counter from home page. User should only be able to reset numerical counter from here 2) when user "Adds Session", the Custom tracker Label should be 0 here. The number should add towards the total here for 2, the log will display the count added each "Add session" | Fail | Done |  |  |  | https://drive.google.com/file/d/1esqNC3jhfUW5g-SwE03gK8ABzPOdOHmg/view?usp=drive_link 1) https://drive.google.com/file/d/1saYgMcZEaiUjt98udmAuvS_pO4_Qe1oW/view?usp=drive_link
| Log | 24/11/2024 | Overview y axis showing decimals instead of whole numbers only | Fail | Done |  |  |  | https://drive.google.com/file/d/1ew79FlecHofKIi443Eu-WUREchmxEhcj/view?usp=drive_link
| Add session (Add media Limitation) | 25/11/2025 | Binded has no media upload capabilities Binded+ will be max 5 pic 3 video max file size 10mb and 100mb | Fail | Done
| Add Session Button Increasing Button Decreasing Button Custom Trackers Note Arrachments Save Button Close Button Back Button Log Button |  |  | Pass
|  | 27/11/24 | Input tracker bar chart sample data 6 weeks | [5 empty] | https://docs.google.com/spreadsheets/d/14GBBhYpOY7LDEnQAl423fxxluvpcIL8wdXPfY41u6PA/edit?gid=0#gid=0
Pass

## 10.DATA DASHBOARD
Checklist:
Scope | Test Case | Last Date Logged | Description | Pass/Fail/Pending-Android | Status | Team comments | Defect Description | Expected result | Media | Dev Query
Data dashboard | Habit dropdown |  |  | Pass
| Habits Chart | 25/11/2024 | The graph in the Habit Data Dashboard is displaying incorrect information. | Fail | Major |  |  | The graph in the Habit Data Dashboard should accurately represen | Image | Can you Guide me with an example of how to calculate history and overview data and how to show in the graph for week, month, and total
| Rewards | 24/11/2024 | The reward dashboard displays a blank page with no content or message available. | Fail | Done |  |  | The reward dashboard should display relevant content such as a list of rewards, options to add new rewards, or a message like "No rewards available" if no data is present, ensuring the page is not left blank. | Image
| Punishments | 24/11/2024 | The Punishments dashboard displays a blank page with no content or message available. | Fail | Done |  |  | The Punishments dashboard should display relevant content or amessage like "No Data available" if no data is present, ensuring the page is not left blank. | Image
| Timer | 24/11/2024 | The timer dashboard is displaying incorrect calculations. | Fail | Major |  |  | The timer dashboard should display accurate calculations, ensuring that all time-related data is correctly summed and presented without discrepancies
| Timer | 24/11/2024 | When changing the preset in the timer dashboard, it should display the results for the newly selected preset, not the previous preset’s results. | Fail | Major |  |  | When changing the preset in the timer dashboard, the results should update to reflect the new preset, and any previous preset results should no longer be displayed. | Video
| Stopwatch | 24/11/2024 | The graph displayed in the stopwatch dashboard is incorrect; it does not correspond to the actual calculations. | Fail | Major |  |  | The graph in the stopwatch dashboard should accurately reflect the correct calculations and display data corresponding to the actual timer results | Image
| Input Tracker | 24/11/2024 | Incorrect average calculation displayed on the graph. | Fail | Major |  |  |  |  | Please can you give me an example of how to calculate displayed on the graph K: 6 weeks data sample. might be messy but almost all there. please double check math. https://docs.google.com/spreadsheets/d/14GBBhYpOY7LDEnQAl423fxxluvpcIL8wdXPfY41u6PA/edit?gid=0#gid=0